## Risk Register
Project Name | Enterprise Cyber Risk Register |  | Risk Impact |  |  | Risk Likelihood |  |  | Risk Response
Project Manager | Simer Preet Kaur |  | 1 | Very Minor |  | 1 | 1 - 20% |  | Avoid
Date Updated | 2026-06-04 |  | 2 | Minor |  | 2 | 21 - 40% |  | Reduce
|  |  | 3 | Moderate |  | 3 | 41 - 60% |  | Fallback
|  |  | 4 | Significant |  | 4 | 61 - 80% |  | Transfer
|  |  | 5 | Catastrophic |  | 5 | 81 - 99% |  | Share
Accept
[5 empty] | Pre Mitigation Scores |  |  | Current Scores |  |  | Post Mitigation Scores
Risk ID | Risk Name | Risk Description | Date Captured | Risk Owner | Pre-Mitigation Impact | Pre-Mitigation Likelihood | Pre-Mitigation Score | Current Impact | Current Likelihood | Current Score | Post-Mitigation Impact | Post-Mitigation Likelihood | Post-Mitigation Score | Risk Response | Mitigation Plan / Actions | Progress | Risk Proximity | Workstream | Operational or Project Risk | Escalation Level | Last Review Date | Next Review Date | Target Completion Date | Historical Progress | Notes
R-001 | Weak Password Practices | Users may create weak passwords leading to unauthorized acces | 2026-06-17 | IAM Manager | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Implement MFA, enforce password complexity requirements, and conduct quarterly access reviews | In Progress | 30 Days | Identity & Access Management | Operational | High | 2026-06-17 | 2026-10-30 | 2026-11-28 | Risk identified and remediation initiated. | Annual review required.
R-002 | Excessive User Privileges | Users retain unnecessary access rights beyond business requirements | 2026-06-18 | IAM Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Apply least privilege principles and perform periodic user access recertification | In Progress | 30 Days | Identity & Access Management | Operational | High | 2026-06-18 | 2026-10-30 | 2026-11-29 | Risk identified and remediation initiated. | Annual review required.
R-003 | Dormant User Accounts | Former employees retain active accounts after termination. | 2026-06-19 | IAM Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Automate account deprovisioning and review inactive accounts monthly | In Progress | 30 Days | Identity & Access Management | Operational | Medium | 2026-06-19 | 2026-11-30 | 2026-12-01 | Risk identified and remediation initiated. | Annual review required.
R-004 | Missing Multi-Factor Authentication | Accounts can be compromised due to lack of MFA | 2026-06-20 | IAM Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Enforce MFA for all users and privileged accounts | In Progress | 30 Days | Identity & Access Management | Operational | Critical | 2026-06-20 | 2026-09-30 | 2026-12-01 | Risk identified and remediation initiated. | Annual review required.
R-005 | Privileged Account Misuse | Administrative accounts may be abused | 2026-06-21 | IAM Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Implement privileged access management and monitor administrator activities | In Progress | 30 Days | Identity & Access Management | Operational | High | 2026-06-21 | 2026-10-30 | 2026-12-02 | Risk identified and remediation initiated. | Annual review required.
R-006 | Unpatched Servers | Critical patches are not applied on time | 2026-06-22 | Infrastructure Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Establish monthly patch management and vulnerability remediation processes | In Progress | 30 Days | Vulnerability Management | Operational | Critical | 2026-06-22 | 2026-09-30 | 2026-12-03 | Risk identified and remediation initiated. | Annual review required.
R-007 | Unsupported Operating Systems | Legacy systems no longer receive security updates | 2026-06-23 | Infrastructure Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Upgrade unsupported systems and remove obsolete assets | In Progress | 30 Days | Vulnerability Management | Operational | High | 2026-06-23 | 2026-10-30 | 2026-12-04 | Risk identified and remediation initiated. | Annual review required.
R-008 | Delayed Security Updates | Delays increase exposure to threats | 2026-06-24 | Infrastructure Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Implement patching SLAs and track compliance through reporting | In Progress | 30 Days | Vulnerability Management | Operational | Medium | 2026-06-24 | 2026-11-30 | 2026-12-05 | Risk identified and remediation initiated. | Annual review required.
R-009 | Unresolved Critical Vulnerabilities | High-risk findings remain open | 2026-06-25 | Vulnerability Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Prioritize remediation of critical findings within defined timelines | In Progress | 30 Days | Vulnerability Management | Operational | Critical | 2026-06-25 | 2026-09-30 | 2026-12-06 | Risk identified and remediation initiated. | Annual review required.
R-010 | Missing Vulnerability Scans | Security weaknesses remain unidentified | 2026-06-26 | Vendor Risk Manager | 3 | 3 | 9 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Schedule automated weekly vulnerability scans | In Progress | 30 Days | Vulnerability Management | Operational | Medium | 2026-06-26 | 2026-11-30 | 2026-12-07 | Risk identified and remediation initiated. | Annual review required.
R-011 | Third-Party Data Breach | Vendor compromise exposes company information | 2026-06-27 | Vendor Risk Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Transfer | Require security assessments, contractual controls and cyber insurance | In Progress | 30 Days | Third-Party Risk Management | Operational | Critical | 2026-06-27 | 2026-09-30 | 2026-12-08 | Risk identified and remediation initiated. | Annual review required.
R-012 | Vendor Lacks Security Certification | Vendor security program is immature | 2026-06-28 | Vendor Risk Manager | 3 | 3 | 9 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Require ISO 27001 certification or equivalent controls | In Progress | 30 Days | Third-Party Risk Management | Operational | Medium | 2026-06-28 | 2026-11-30 | 2026-12-09 | Risk identified and remediation initiated. | Annual review required.
R-013 | Inadequate Vendor Assessments | Third-party risks are not properly reviewe | 2026-06-29 | Vendor Risk Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Perform annual vendor risk assessments and control reviews | In Progress | 30 Days | Third-Party Risk Management | Operational | Medium | 2026-06-29 | 2026-11-30 | 2026-12-10 | Risk identified and remediation initiated. | Annual review required.
R-014 | Vendor Business Failure | Vendor becomes unavailable or insolvent | 2026-06-30 | Vendor Risk Manager | 4 | 2 | 8 | 2 | 1 | 2 | 1 | 1 | 1 | Transfer | Maintain alternate suppliers and business continuity plans | In Progress | 30 Days | Third-Party Risk Management | Operational | Medium | 2026-06-30 | 2026-11-30 | 2026-12-11 | Risk identified and remediation initiated. | Annual review required.
R-015 | Vendor Access Misuse | Vendor employees misuse privileged access | 2026-07-01 | Vendor Risk Manager | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Restrict vendor access and monitor third-party activities | In Progress | 30 Days | Third-Party Risk Management | Operational | High | 2026-07-01 | 2026-10-30 | 2026-12-12 | Risk identified and remediation initiated. | Annual review required.
R-016 | Misconfigured Cloud Storage | Sensitive data becomes publicly accessible | 2026-07-02 | Cloud Security Lead | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Implement secure configuration baselines and CSPM monitoring | In Progress | 30 Days | Cloud Security | Operational | Critical | 2026-07-02 | 2026-09-30 | 2026-12-13 | Risk identified and remediation initiated. | Annual review required.
R-017 | Publicly Accessible Resources | Cloud assets exposed to the internet | 2026-07-03 | Cloud Security Lead | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Conduct periodic reviews of cloud exposure settings | In Progress | 30 Days | Cloud Security | Operational | High | 2026-07-03 | 2026-10-30 | 2026-12-14 | Risk identified and remediation initiated. | Annual review required.
R-018 | Insufficient Cloud Monitoring | Security incidents may go undetected | 2026-07-04 | Cloud Security Lead | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Enable centralized logging and real-time monitoring | In Progress | 30 Days | Cloud Security | Operational | Medium | 2026-07-04 | 2026-11-30 | 2026-12-15 | Risk identified and remediation initiated. | Annual review required.
R-019 | Insecure Cloud Configuration | Security settings do not meet standards | 2026-07-05 | Cloud Security Lead | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Enforce cloud security standards and automated compliance checks | In Progress | 30 Days | Cloud Security | Operational | High | 2026-07-05 | 2026-10-30 | 2026-12-16 | Risk identified and remediation initiated. | Annual review required.
R-020 | Weak Cloud Access Controls | Excessive permissions increase risk | 2026-07-06 | Cloud Security Lead | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Implement role-based access controls and periodic reviews | In Progress | 30 Days | Cloud Security | Operational | High | 2026-07-06 | 2026-10-30 | 2026-12-17 | Risk identified and remediation initiated. | Annual review required.
R-021 | ISO 27001 Non-Compliance | Controls do not meet framework requirements | 2026-07-07 | Compliance Manager | 4 | 4 | 16 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Perform annual internal audits and compliance reviews | In Progress | 30 Days | Compliance & Audit | Operational | High | 2026-07-07 | 2026-10-30 | 2026-12-18 | Risk identified and remediation initiated. | Annual review required.
R-022 | Missing Audit Evidence | Audit requirements cannot be demonstrated | 2026-07-08 | Compliance Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Establish centralized audit evidence repositories | In Progress | 30 Days | Compliance & Audit | Operational | Medium | 2026-07-08 | 2026-11-30 | 2026-12-19 | Risk identified and remediation initiated. | Annual review required.
R-023 | Incomplete Risk Assessments | Risks are not fully identified or evaluated | 2026-07-09 | GRC Analyst | 3 | 3 | 9 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Conduct quarterly risk assessments and management reviews | In Progress | 30 Days | Compliance & Audit | Operational | Medium | 2026-07-09 | 2026-11-30 | 2026-12-20 | Risk identified and remediation initiated. | Annual review required.
R-024 | Policy Review Overdue | Policies become outdated and ineffective | 2026-07-10 | Compliance Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Create annual policy review and approval schedules | In Progress | 30 Days | Compliance & Audit | Operational | High | 2026-07-10 | 2026-10-30 | 2026-12-21 | Risk identified and remediation initiated. | Annual review required.
R-025 | Regulatory Compliance Failure | Non-compliance may result in penalties | 2026-07-11 | Compliance Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Track regulatory obligations and implement compliance monitoring | In Progress | 30 Days | Compliance & Audit | Operational | High | 2026-07-11 | 2026-10-30 | 2026-12-22 | Risk identified and remediation initiated. | Annual review required.
R-026 | Delayed Incident Reporting | Security incidents are not escalated quickly | 2026-07-12 | SOC Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Define escalation procedures and incident notification requirements | In Progress | 30 Days | Incident Response | Operational | Medium | 2026-07-12 | 2026-11-30 | 2026-12-23 | Risk identified and remediation initiated. | Annual review required.
R-027 | Ineffective Incident Response Process | Incident containment is delayed | 2026-07-13 | SOC Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Update incident response plans and conduct testing | In Progress | 30 Days | Incident Response | Operational | High | 2026-07-13 | 2026-10-30 | 2026-12-24 | Risk identified and remediation initiated. | Annual review required.
R-028 | Lack of Tabletop Exercises | Teams are unprepared for cyber events | 2026-07-14 | SOC Manager | 3 | 3 | 9 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Conduct annual tabletop exercises involving key stakeholders | In Progress | 30 Days | Incident Response | Operational | Medium | 2026-07-14 | 2026-11-30 | 2026-12-25 | Risk identified and remediation initiated. | Annual review required.
R-029 | Inadequate Security Monitoring | Threats remain undetected | 2026-07-15 | SOC Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Implement SIEM monitoring and alerting capabilities | In Progress | 30 Days | Incident Response | Operational | Critical | 2026-07-15 | 2026-09-30 | 2026-12-26 | Risk identified and remediation initiated. | Annual review required.
R-030 | Missing Incident Documentation | Investigation records are incomplete | 2026-07-16 | SOC Manager | 3 | 3 | 9 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Standardize incident reporting templates and evidence collection | In Progress | 30 Days | Incident Response | Operational | Medium | 2026-07-16 | 2026-11-30 | 2026-12-27 | Risk identified and remediation initiated. | Annual review required.
R-031 | Backup Failure | Critical backup jobs fail | 2026-07-17 | BCDR Manager | 5 | 4 | 20 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Test backups monthly and monitor backup success rates | In Progress | 30 Days | Business Continuity & Disaster Recovery | Operational | Critical | 2026-07-17 | 2026-09-30 | 2026-12-28 | Risk identified and remediation initiated. | Annual review required.
R-032 | Disaster Recovery Plan Not Tested | Recovery capabilities are unverified | 2026-07-18 | BCDR Manager | 5 | 3 | 15 | 3 | 2 | 6 | 2 | 1 | 2 | Reduce | Conduct annual disaster recovery exercises | In Progress | 30 Days | Business Continuity & Disaster Recovery | Operational | High | 2026-07-18 | 2026-10-30 | 2026-12-29 | Risk identified and remediation initiated. | Annual review required.
R-033 | Data Center Outage | Facility disruption causes downtime | 2026-07-19 | Infrastructure Manager | 5 | 2 | 10 | 2 | 2 | 4 | 1 | 1 | 1 | Transfer | Implement redundant infrastructure and failover capabilities | In Progress | 30 Days | Business Continuity & Disaster Recovery | Operational | Medium | 2026-07-19 | 2026-11-30 | 2026-12-30 | Risk identified and remediation initiated. | Annual review required.
R-034 | Single Point of Failure | No redundancy exists for critical systems | 2026-07-20 | Infrastructure Manager | 4 | 3 | 12 | 2 | 2 | 4 | 1 | 1 | 1 | Reduce | Build redundancy for critical systems and services | In Progress | 30 Days | Business Continuity & Disaster Recovery | Operational | Medium | 2026-07-20 | 2026-11-30 | 2026-12-31 | Risk identified and remediation initiated. | Annual review required.

## Lookups
Risk Impact |  |  | Risk Likelihood |  |  |  | Risk Response
1 | Very Minor |  | 1 | 1 - 20% |  |  | Avoid
2 | Minor |  | 2 | 21 - 40% |  |  | Reduce
3 | Moderate |  | 3 | 41 - 60% |  |  | Fallback
4 | Significant |  | 4 | 61 - 80% |  |  | Transfer
5 | Catastrophic |  | 5 | 81 - 99% |  |  | Share
Accept
| Impact | 5 | 10 | 15 | 20 | 25
|  | 4 | 8 | 12 | 16 | 20
|  | 3 | 6 | 9 | 12 | 15
|  | 2 | 4 | 6 | 8 | 10
|  | 1 | 2 | 3 | 4 | 5
Likelihood