## Executive Summary
ISO 27001 Compliance Assessment & Remediation Program
Organization: ABC Financial Services | Top Findings
• MFA not enforced
Industry: Financial Services | • Vendor security reviews not documented
• Cloud security baseline not defined
Employees: 250 | • No centralized monitoring solution
• Backup restore testing not validated
Environment:
Microsoft 365
Microsoft Azure
Assessment Date:
2026-08-01
|  | Severity | Count
Controls Assessed: 15
|  | HIgh | 9
High Risk Findings: 9 |  | Medium | 6
Medium Risk Findings: 6
Current Compliance Score: 72%
Target Compliance Score: 95%
Overall Assessment: Partially Compliant
Assessment Outcome:
High-priority remediation activities have been identified.
Implementation of recommended controls is expected to improve
overall compliance from 72% to 95%.
Assessment Scope:
- Identity & Access Management
- Cloud Security
- Vendor Risk Management
- Compliance & Audit
- Incident Response
- Business Continuity
Assessment Outcome:
High-priority remediation activities required to achieve target compliance level.

## Gap Assessment
Gap ID | ISO Control | Control Name | Current State | Gap Found | Risk Level | Business Impact | Recommendation | Owner | Status
G-001 | A.5.17 | Authentication Information | MFA not enforced across business applications | Yes | High | Unauthorized account access and potential compliance violations. | Implement MFA for all users | IAM Manager | Open
G-002 | A.5.18 | Access Rights | Access reviews not conducted quarterly | Yes | High | Excessive access may lead to unauthorized data exposure. | Establish quarterly access reviews | IAM Manager | Open
G-003 | A.5.19 | Supplier Relationships | Vendor security reviews not documented | Yes | High | Third-party compromise may impact confidentiality of organizational data. | Create vendor assessment process | Vendor Risk Manager | Open
G-004 | A.5.23 | Security for Cloud Services | Cloud security baseline not defined | Yes | High | Misconfigured cloud environments may expose sensitive information. | Implement cloud security standards | Cloud Security Lead | Open
G-005 | A.5.30 | ICT Readiness for Business Continuity | DR testing not performed | Yes | High | Business disruption and extended recovery during disaster events. | Conduct annual DR testing | BCDR Manager | Open
G-006 | A.6.3 | Information Security Awareness | Security training not mandatory | Yes | Medium | Increased risk of phishing and social engineering incidents. | Launch annual awareness training | Security Awareness Lead | Open
G-007 | A.8.15 | Logging | Log retention period insufficient | Yes | Medium | Limited ability to support investigations and audits. | Increase retention to 1 year | SOC Manager | Open
G-008 | A.8.16 | Monitoring Activities | No centralized monitoring solution | Yes | High | Delayed detection and response to security incidents. | Implement SIEM platform | SOC Manager | Open
G-009 | A.8.8 | Management of Technical Vulnerabilities | Vulnerability scans performed quarterly only | Yes | High | Critical vulnerabilities may remain unidentified and exploitable. | Perform monthly scans | Vulnerability Manager | Open
G-010 | A.5.31 | Legal, Statutory and Regulatory Requirements | Compliance obligations not tracked | Yes | Medium | Potential regulatory fines and legal exposure. | Develop compliance tracking register | Compliance Manager | Open
G-011 | A.5.24 | Information Security Incident Management | Tabletop exercises not performed | Yes | Medium | Incident response teams may be unprepared during cyber events. | Conduct annual tabletop exercises | SOC Manager | Open
G-012 | A.5.9 | Inventory of Information Assets | Asset inventory incomplete | Yes | Medium | Lack of visibility into organizational assets and risks. | Complete asset inventory | IT Manager | Open
G-013 | A.5.17 | Password Controls | Password complexity settings weak | Yes | High | Weak passwords may increase account compromise risk. | Strengthen password policy | IAM Manager | Open
G-014 | A.5.30 | Backup Management | Backup restore testing not validated | Yes | High | Data loss and recovery failures during service disruptions. | Perform monthly backup testing | BCDR Manager | Open
G-015 | Clause 9 | Internal Audit Evidence | Audit evidence repository missing | Yes | Medium | Increased risk of unauthorized access and sensitive data exposure. | Implement evidence repository | Compliance Manager | Open

## Remediation Roadmap
Gap ID | Remediation Action | Priority | Owner | Target Date | Status | Estimated Cost
G-001 | Implement MFA | High | IAM Manager | 2026-09-30 | Open | 15000
G-002 | Quarterly Access Reviews | High | IAM Manager | 2026-09-30 | Open | 5000
G-003 | Vendor Assessment Process | High | Vendor Risk Manager | 2026-10-31 | Open | 8000
G-004 | Cloud Security Baseline | High | Cloud Security Lead | 2026-10-31 | Open | 12000
G-005 | Disaster Recovery Testing | High | BCDR Manager | 2026-10-31 | Open | 10000
G-006 | Security Awareness Program | Medium | Security Awareness Lead | 2026-11-30 | Open | 3000
G-007 | Log Retention Enhancement | Medium | SOC Manager | 2026-11-30 | Open | 4000
G-008 | SIEM Implementation | High | SOC Manager | 2026-10-31 | Open | 18000
G-009 | Monthly Vulnerability Scanning | High | Vulnerability Manager | 2026-10-31 | Open | 6000
G-010 | Compliance Tracking Register | Medium | Compliance Manager | 2026-11-30 | Open | 2500
G-011 | Tabletop Exercises | Medium | SOC Manager | 2026-11-30 | Open | 2000
G-012 | Asset Inventory Update | Medium | IT Manager | 2026-11-30 | Open | 3500
G-013 | Password Policy Enhancement | High | IAM Manager | 2026-10-31 | Open | 2500
G-014 | Backup Validation Program | High | BCDR Manager | 2026-10-31 | Open | 5000
G-015 | Audit Evidence Repository | Medium | Compliance Manager | 2026-11-30 | Open | 3000